## Slide 1: Scheduling
Project Planning
Create a Project Plan
Created by: Vande Ven, Susan and Morrow, Darin, Kennesaw State University

## Slide 2: Key to Success
PLANNING!
  It saves time, money, frustration, etc.
  "Project plan" is a set of living documents that can be expected to change over the life of the project.
  A place to deviate from if needed
  Hope is not a PLAN
  Explain the project plan to all stakeholders

## Slide 3: Project Scope Statement
Most important document in the project plan.
Comprehensive - decreases the chances of miscommunication.
The scope statement should include:
  Business needs
  Project objectives
  Benefits of completing the project,
  Which deliverables will be included or excluded from the project
In a way, its a contract between the project manager and sponsor - one that can only be changed with sponsor approval.
Define what is in and out of scope – be clear and specific
Keeping scope at evey stage of the project is critical

## Slide 4: Project Scope Statement - Example
One Example
Project Scope Example [Online Image] Retrieved March 16,2022 from https://templatelab.com/project-scope/

## Slide 5: Work Breakdown Structure
“A work breakdown structure defines all the things a project needs to accomplish, organized into multiple levels, and displayed graphically.”
Work Breakdown Schedule More Info

## Slide 6: Work Breakdown Discussion
Work Breakdown Structure includes:
Dividing a large and complex project into simpler, manageable and independent tasks.
The root of this tree (structure) is labelled by the Project name itself.
For constructing a work breakdown structure,
  Each node is recursively decomposed into smaller sub-activities,
  Until at the leaf level,
  Activities becomes undividable and independent.
It follows a Top-Down approach.
Steps:
Step-1: Identify the major activities of the project.
Step-2: Identify the sub-activities of the major activities.
Step-3: Repeat till undividable, simple and independent activities are created.

## Slide 7: Work Breakdown Discussion
Work Breakdown Structure [Online Image] Retrieved October 3, 2022, from https://www.geeksforgeeks.org/software-engineering-work-breakdown-structure/

## Slide 8: Work Breakdown Examples
Work Breakdown Structure [Online Image] Retrieved October 3, 2022, fromhttps://blog.ganttpro.com/en/work-breakdown-structure-example-wbs/

## Slide 9: How to Create a Work Breakdown Structure
Determine the major deliverables or products to be produced. ...
Divide each of these major deliverables into its component deliverables in the same manner. ...
Divide each of these work pieces into its component parts.

## Slide 10: Components of the project plan
Project's starting points:
  It’s the PM’s job to costs associates with achieving results.
  That’s is true but – it will take many people to really get there.
Scope
  Maintain scope
  Change Control (Module 5) - be strict

## Slide 11: Components of the project plan
Schedule
  For each phase
  For each task
  For each sub task
Cost
  For each phase
  For each task
  For each sub task
Performance
If you must be able to measure whether the project is on track during execution

## Slide 12: Project Schedule
Create a list of tasks that need to performed. For each task determine the following:
  The amount of effort (hours or days) required for completing the task
  The resource needed to finish the task
  Established an accurate delivery date for each task.
  Input all the tasks, durations and the resources needed to complete each task.

## Slide 13: Schedule and cost baselines
Develop a work breakdown structure (WBS) Identify activities and tasks, all the work to be done
Estimate how many hours it will take to complete each task
Estimate cost of each task
Consider how much time each resource can be devote to this one project
Develop critical path
Develop schedule, which puts all tasks and estimates in a calendar.
Develop a cost-by-time period

## Slide 14: Project Deliverables
Create a list of things needed to the project to meet those goals. Examples
  Requirements
  Design + Reviews
  Software
    UI/UX
    Database
    APIs
    Etc.
    Code Reviews
    Unit testing
  Test Plan
  Deployment Plan

## Slide 15: Project Deliverables
Specify when and how to deliver each item
  When can it start
  How long will it take
    What's the size and complexity of the work
      Small, Med, large (define that)
      Easy, Moderate, Complex
      The combination determines the length of time (e.g. Large and complex takes more time than easy and small
    How long does it take
    Who can do the work
Add the deliverables to the project plan with an estimated delivery date.
  List the tasks to be done
  Who will do it
  When is it do
  Checkpoints so you know you are on track

## Slide 16: Roles and Responsibilities
What resources are part of the project
  Skills – UI/UX, Database Developer, ????
  Roles – PM, Design Lead
Who are those resources
  Are they currently on the team
  Do we need to hire employees or contractors

## Slide 17: Estimation Methods
Estimating is difficult but you will have to estimate
  SCOPE must be known otherwise you are guessing
  (and yes, they may ask you to guess)
Analogous (Past Experience)
  Use similar projects (scope and timeline) to use a basis
  Look for new technologies
3 step process
  Best case (never happens)
  Most likely/probable
  Worst Case (what you use when forced to guess)
Most companies will have a process (formal or informal)
  Functional changes (new, existing) – small, medium, large
  Interfaces changes (new, existing) – small, med, large

## Slide 18: A common problem
Sponsor imposing a delivery deadline that is not realistic based on your estimates.
The options you have in this situation are:
  Renegotiate the deadline (project delay)
  Employ additional resources (increased cost)
  Reduce the scope of the project (less delivered)
  Note: Use the project schedule to justify pursuing one of these options.

## Slide 19: Supporting Plans
Human Resource Plan
Identify, by name, number, type of people, their roles and responsibilities to carry out the project.
Put the start dates, the duration and the method you will use for obtaining them.

## Slide 20: Management Plans
Not all new requests will result in changes to the scope, schedule or budget, but a process is needed to study all new requests to determine their impact on the project.
Different approval levels are usually needed for different types of changes.

## Slide 21: Communications
Who wants which reports, how often, in what format and using what media
How issues will be escalated and when
Where project information will be stored and who can access it
What new risks have surfaced
What metrics will be used to ensure a quality product is built

## Slide 22: Communications Plan
Create a document showing who is to be kept informed about the project.
  Project Stakeholders
  Project Team members
  Project Status
How they will receive the information.
Have weekly or bi-weekly reports

## Slide 23: Risk Management Plan
You will have risks – How will you mitigate?
  Time and cost estimate too optimistic
    Most people plan too little time and too little $$
  Customer review and feedback cycle too slow
    Reviews and sign offs
  Unexpected budget cuts
    Funding can become an issue

## Slide 24: Risk Management Plan
You will have risks – How will you mitigate?
  Unclear roles and responsibilities
    Who are decision makers
  No stakeholder input obtained
    Poor Requirements
  Not clearly understanding stakeholder needs
    Poor Requirements
  Changing requirements after the project has started
    Change Control

## Slide 25: Risk Management Plan Continued
Risks can be tracked using a risk log.
  Risk must be clear
  Risk must have a risk owner
  Risk must have a mitigation plan
  Risks must be reviewed at stakeholder level
Review your risk log on a regular basis.
  Resolve you Risks on a regular basis
  Tracking risks doesn’t resolve risks
Remember, if you ignore risks, they don't go away.
  Go well for you – IT WILL NOT!

## Slide 26: Congratulations!
Follow all the steps above & you should have a good project plan.
Don't forget to update and adjust your plan as the project progress
Keep measuring progress against the plan.
Developing a clear and executable project plan takes time and effort.
Don’t skip planning and jump straight into execution.